One Fintech — FIS Prepaid Sunrise

Batch ETL Integration — Session Handoff

HANDOFF_2026-03-18_OneFin-FIS-Batch-Implementation_v01-01-00

| Date | 2026-03-18 |
| --- | --- |

| Repo | Walker-Morse/Batch (GitHub), branch main |
| --- | --- |

| Base commit | ee70494 (inherited from prior session) |
| --- | --- |

| This session commits | d1d84778, 1b4dd009, c81dbf55, a883f82b, c4edd83e, ec3367d6, f7609149, e2ad6833, 73e9f81e, ac372acb, 1b821adf |
| --- | --- |

| Language | Go 1.22 |
| --- | --- |

| Test baseline | 60 passing (inherited) + 4 new program lookup unit tests |
| --- | --- |

| Go-Live Target | June 1, 2026 — RFU programme start July 1, 2026 |
| --- | --- |

# 1. What Was Done This Session

Two critical gaps blocking the first real file run were closed: program lookup (the FK blocker) and the FIS sequence counter (the duplicate filename blocker).

## 1.1 Program Lookup Gap — Closed

processSRG310Row previously passed a zero UUID as consumers.program_id, causing a FK violation on every real file. The fix has four parts:

GetProgramByTenantAndSubprogram added to DomainStateRepo (_adapters/aurora/domain_state.go). Queries programs WHERE tenant_id=$1 AND fis_subprogram_id=$2 AND is_active=true. Returns uuid.UUID or error.

ProgramLookup interface added to _shared/ports/ports.go — single-method, narrow interface. Allows Stage 3 to be unit-tested without a live DB.

RowProcessingStage.lookupProgram() added to stage3_row_processing.go. Calls s.Programs (the interface), memoises results in programCache map[string]uuid.UUID keyed by tenantID+"|"+subprogramID. At most one DB round-trip per unique subprogram per file (RFU files are 100% one subprogram — one hit total).

Row.SubprogramID (string from CSV, e.g. "26071") is parsed to int64 via strconv.ParseInt for the RT30 batch record. consumer.ProgramID is now the resolved UUID, not zero.

If the subprogram is not found in programs, the row is dead-lettered with failure_reason=program_lookup_failed(subprogram=X) — not a file abort.

main.go wired: domainStateRepo passed as both DomainState and Programs fields. Zero-UUID TODO comment removed.

## 1.2 FIS Sequence Counter — Implemented

dbSequenceStore.Next() previously returned hardcoded 1. FIS silently discards files with duplicate names (§6.5.5). The fix:

_schema/pipeline_state/005_fis_sequence.sql adds fis_file_sequence(program_id, sequence_date) table and NextFISSequence() PostgreSQL function. Atomic INSERT...ON CONFLICT DO UPDATE — safe under concurrent Fargate tasks.

_adapters/aurora/fis_sequence.go implements FISSequenceRepo satisfying fis_adapter.SequenceStore. Parses programID string to UUID, calls NextFISSequence(), rejects sequences > 99 (FIS two-digit filename field limit) with an error that halts the pipeline.

main.go: dbSequenceStore stub removed. aurora.NewFISSequenceRepo(pool) wired in its place.

Schema execution order: add 005_fis_sequence.sql after 004_dead_letter_store.sql during DEV provisioning (programs FK dependency).

## 1.3 Unit Tests — 4 New Tests

member_enrollment/pipeline/stage3_program_lookup_test.go added. Tests in package pipeline (same-package access to unexported methods).

MockProgramLookup, MockDeadLetterRepository, MockDomainCommandRepository added to _shared/testutil/mocks.go.

Four tests: ReturnsKnownProgramID (happy path), CachesResult (5 calls → 1 DB hit), DeadLettersOnUnknownProgram (dead-letter path, not abort), MultipleSubprograms (two distinct subprograms → two DB hits, each cached).

Note: end-to-end processSRG310Row tests require a live DB (DomainStateRepo and BatchRecordsRepo are concrete types, not interfaces). Those are integration tests for a future suite.

# 2. Current State

## 2.1 Known Gaps Before First Real File Can Run

| Status | Item | Notes |
| --- | --- | --- |
| ✓ DONE | Program lookup | GetProgramByTenantAndSubprogram wired. Per-row cache. Dead-letters unknown subprogram. |
| ✓ DONE | FIS sequence counter | FISSequenceRepo + NextFISSequence(). Durable, atomic, max-99 guard. |
| ○ TODO | Assembler queries DB | AssembleFile builds valid but empty file. Needs BatchRecordsRepo.ListStagedByCorrelationID(). Next highest priority for first real file. |
| ○ TODO | Real PGP decrypt (Stage 2) | NullPGPDecrypt passthrough. Needs golang.org/x/crypto wired from Secrets Manager. |
| ○ TODO | Real PGP encrypt (Stage 4) | NullPGPEncrypt passthrough. Needs FIS public key from Secrets Manager. |
| ○ TODO | fis_card_id RT37/RT60 | fisCardIDOrEmpty() always returns empty. Correct for first-time enrollments — RT30 must arrive first. |
| ○ TODO | UpdatePurseBalance | Commented TODO in Stage 3. FBO integrity requirement (Addendum I). Must complete before go-live. |
| ○ TODO | DEV AWS environment | No real runs possible. Target Apr 6. |

## 2.2 Pipeline Stage Status

| Status | Item | Notes |
| --- | --- | --- |
| ✓ DONE | Stage 1 — File Arrival | SHA-256, batch_files write, audit_log. Tested. |
| ✓ DONE | Stage 2 — Validation | PGP passthrough, SRG parse, dead-letter malformed rows. |
| ✓ DONE | Stage 3 — Row Processing | Idempotency gate, RT30/37/60 staging, domain state, program lookup. |
| ✓ DONE | Stage 4 — Batch Assembly | FIS assembler, PGP passthrough, S3 write, plaintext delete. |
| ○ TODO | Stage 5 — FIS Transfer | Struct defined, Run() is stub. Apr 27 target. |
| ○ TODO | Stage 6 — Return File Wait | S3 polling, 6h timeout (Open Item #25). Stub. |
| ○ TODO | Stage 7 — Reconciliation | Return file parse, RT99 halt, MCO report. Stub. |

# 3. Test Coverage

| Status | Item | Notes |
| --- | --- | --- |
| 60 (inherited) | All prior tests | go test clean across all packages. |
| +4 new | stage3_program_lookup_test.go | lookupProgram: cache, happy path, dead-letter, multi-subprogram. |
| Not yet tested | Aurora adapters (integration) | Require live DB. fis_sequence.go, domain_state.go, batch_files.go. |
| Not yet tested | Stages 2/3/4 full run | Mocks needed for BatchRecordsRepo and DomainStateRepo concrete types. |

# 4. How to Start Next Session

Read memory edits first. Then:

| Step 1 | Clone/pull Walker-Morse/Batch on main. Run make test — expect 64 passing. |
| --- | --- |

| Step 2 | Run 005_fis_sequence.sql against DEV Aurora (after programs table exists). Verify NextFISSequence(program_uuid, today) returns 1. |
| --- | --- |

| Step 3 (highest priority for first real file) | Implement BatchRecordsRepo.ListStagedByCorrelationID(). Wire result into AssembleFile in assembler_impl.go so RT30/37/60 records are queried and included. Without this, the assembled file is structurally valid but empty. |
| --- | --- |

| Step 4 (Apr 27 target) | Implement Stages 5–7: _adapters/sftp/ for FIS Transfer Family, stage5_fis_transfer.go, stage6_return_file_wait.go, stage7_reconciliation.go. |
| --- | --- |

| Step 5 | Run make test. All tests must pass. Add tests for new logic before declaring done. |
| --- | --- |

| Step 6 | Commit with descriptive message. No session ends without a commit. |
| --- | --- |

Morse LLC — Speak Benefits — One Fintech | “Boring technology, radical purpose.”